{"text_format":"1","workbook":"xlsx","n_sheets":6,"sheets":["Map","Schedule","Graphic Overview","Help","Data","Map_Backup"],"not_rendered":{"charts":0,"images":4,"macros":1,"external_links":0,"defined_names":2,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Map","index":0,"n_rows":101,"n_cols":1,"rows_kept":101,"cut":false,"hidden":false,"merged":[[100,0,100,3]]}
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["Last update: 12 January 2021"]

{"sheet":"Schedule","index":1,"n_rows":56,"n_cols":34,"rows_kept":56,"cut":false,"hidden":false,"merged":[[1,31,2,31],[1,32,2,32],[1,33,2,33],[1,23,1,27],[1,5,1,6],[1,7,1,8],[1,9,1,10],[1,11,1,12],[1,13,1,14],[1,18,1,22]]}
[null,10000]
[null,"IM","ID","Section","Direction","Line",null,"Year",null,"Week",null,"Period from",null,"Period to",null,"Duration","Time \nof day","Reason for \nrestriction","Traffic impact",null,null,null,null,"Traffic measures",null,null,null,null,"Description","International coordination",null,"IM\nProject ID\n(Optional)","Last update","cancelled"]
[null,null,null,null,null,"From","To","From","To","From","To","Date from","Time from","Date to","Time to",null,null,null,"Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Rerouting","Train replacement","Delays","Other",null,null,"In yearly timetable"]
[null,"PKP PLK-SA","51_11_2301","Oświęcim - Kraków","<","Dwory","Oświęcim",2023,2023,46,11,"2023-05-13","00:00:00","2023-09-12",1,"123 days","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"renewal",null,"Y",null,"2023-07-17","N"]
[null,"PKP PLK-SA","51_11_213","Oświęcim - Kraków",">","Podbory Skawińskie","Brzeźnica",2023,2023,24,50,"2023-09-02","00:00:00","2023-12-22",1,"112 days","continuous","Miscellaneous",null,"LT","S",null,null,null,null,null,null,null,"renewal",null,"Y",null,"2023-07-17","N"]
[null,"PKP PLK-SA","51_11_214","Tunel - Radom","<","Jędrzejów","Sędziszów",2025,2027,52,18,"2025-06-12","00:00:00","2027-01-09",1,"576 days","continuous","Miscellaneous","T","LT",null,null,null,null,null,null,null,null,"renewal and modernization",null,"N",null,"2023-12-17","N"]
[null,"PKP PLK-SA","51_11_2303","Katowice - Tunel","<","Jaroszowiec Olkuski","Olkusz",2024,2024,13,18,"2024-06-10","00:00:00","2024-12-05",1,"178 days","continuous","Miscellaneous","T","LT","S",null,null,null,null,null,null,null,"renewal; 6 hours total closure during night",null,"Y",null,"2023-12-17","N"]
[null,"PKP PLK-SA","51_11_2305","Tunel - Radom","<","Radkowice","Wolica",2023,2025,18,31,"2023-12-10","00:00:00","2025-06-11",1,"364 days ","continuous","Track & Rail",null,"LT","S",null,null,null,null,null,null,null,"modernization",null,"Y",null,"2023-07-17","N"]
[null,"ŽSR","56KE2212130","Hidasnémeti - Košice ","< >","Čierna nad Tisou št. hr.","Varín",2024,2024,1,48,"2024-01-01","08:00:00","2024-11-30",0.66666666666666663,"334 days","periodical","Signal",null,null,null,null,null,null,null,null,null,null,"GSM-R 101, 105",null,null,null,"2022-12-07"]
[null,"ŽSR","56KE2212132","Hidasnémeti - Košice ","< >","Nižná Myšľa","Ruskov",2024,2026,35,18,"2024-09-01","08:00:00","2026-04-30",0.66666666666666663," days","periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"101",null,null,null,"2023-06-23"]
[null,"ŽSR","56KE2212133","Hidasnémeti - Košice ","< >","Košice"," Košice",2024,2024,1,53,"2024-01-01","08:00:00","2024-12-31",0.66666666666666663,"365 days","periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"101, 10",null,null,null,"2022-12-07"]
[null,"ŽSR","56ZA2212063","Žilina - Skalité","< >","Žilina","Žilina",2024,2024,1,35,"2024-01-01","08:00:00","2024-08-31",0.66666666666666663,"243 days","periodical","Miscellaneous",null,null,null,null,null,null,null,null,null,null,"106, 114",null,null,null,"2022-12-07"]
[null,"MAV",5511140001,"Kiskunhalas - Budapest","< >","Cegléd","Kecskemét",2024,2024,9,9,"2024-03-02","23:45:00","2024-03-03",0.1875,"1 days + -19 h 45 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140002,"Kiskunhalas - Szolnok","< >","Cegléd","Kecskemét",2024,2024,9,10,"2024-03-03","23:45:00","2024-03-04",0.1875,"1 days + -19 h 45 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140003,"Kiskunhalas - Szolnok","< >","Cegléd","Kecskemét",2024,2024,10,10,"2024-03-04","23:45:00","2024-03-05",0.1875,"1 days + -19 h 45 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140004,"Kiskunhalas - Szolnok","< >","Kecskemét","Kiskunfélegyháza",2024,2024,10,10,"2024-03-05","22:30:00","2024-03-06",0.16666666666666666,"1 days + -18 h 30 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140005,"Kiskunhalas - Szolnok","< >","Kecskemét","Kiskunfélegyháza",2023,2024,11,10,"2023-03-06","22:30:00","2024-03-07",0.16666666666666666,"367 days + -18 h 30 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140006,"Kiskunhalas - Szolnok","< >","Kecskemét","Kiskunfélegyháza",2024,2024,10,10,"2024-03-07","22:30:00","2024-03-08",0.16666666666666666,"1 days + -18 h 30 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140007,"Kiskunhalas - Szolnok","< >","Cegléd","Kecskemét",2024,2024,36,36,"2024-09-07","23:45:00","2024-09-08",0.1875,"1 days + -19 h 45 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140008,"Kiskunhalas - Szolnok","< >","Cegléd","Kecskemét",2024,2024,36,37,"2024-09-08","23:45:00","2024-09-09",0.1875,"1 days + -19 h 45 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140009,"Kiskunhalas - Szolnok","< >","Cegléd","Kecskemét",2024,2024,37,37,"2024-09-09","23:45:00","2024-09-10",0.1875,"1 days + -19 h 45 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140010,"Kiskunhalas - Szolnok","< >","Kecskemét","Kiskunfélegyháza",2024,2024,37,37,"2024-09-10","22:30:00","2024-09-11",0.16666666666666666,"1 days + -18 h 30 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140011,"Kiskunhalas - Szolnok","< >","Kecskemét","Kiskunfélegyháza",2024,2024,37,37,"2024-09-11","22:30:00","2024-09-12",0.16666666666666666,"1 days + -18 h 30 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511140012,"Kiskunhalas - Szolnok","< >","Kecskemét","Kiskunfélegyháza",2024,2024,37,37,"2024-09-12","22:30:00","2024-09-13",0.16666666666666666,"1 days + -18 h 30 min","continuous","Others","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511150001,"Kiskunhalas - Budapest","< >","Soroksár","Kiskunhalas",2023,2024,50,50,"2023-12-10","00:00:00","2024-12-14",0.99930555555555556,"370 days + 23 h 59 min","continuous","Track & Rail","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"MAV",5511150002,"Kelebia - Kiskunhalas","< >","Kiskunhalas","Kelebia",2023,2024,50,50,"2023-12-10","00:00:00","2024-12-14",0.99930555555555556,"370 days + 23 h 59 min","continuous","Track & Rail","T",null,null,null,null,null,"R",null,"D",null,"Total closer",null,null,null,"2022-08-23"]
[null,"GySEV/Raaberbahn",null,"Szombathely - Sopron","< >","Szombathely","Acsád",2023,2024,50,5,"2023-12-10",null,"2024-01-31",null,"52 days","continuous","Signal",null,null,null,null,null,null,null,null,null,null,"New path can't be ordered",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Szombathely - Csorna","< >","Szombathely","Vép",2023,2024,50,5,"2023-12-10",null,"2024-01-31",null,"52 days","continuous","Signal",null,null,null,null,null,null,null,null,null,null,"New path can't be ordered",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Csorna - Rajka","< >","Csorna","Hegyeshalom",2024,2024,15,18,"2024-04-08",null,"2024-04-30",null,"22 days","continuous","Maintenance","T",null,null,null,null,null,"R",null,null,null,"Catenary maintenance and ballast tamping",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Csorna - Komárom","< >","Csorna","Győr",2024,2024,19,20,"2024-05-06",null,"2024-05-13",null,"7 days","continuous","Catenary",null,null,null,null,null,null,null,null,null,null,"Catenary maintenance",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Szombathely - Csorna","< >","Porpác","Répcelak",2024,2024,22,22,"2024-05-27",null,"2024-05-31",null,"4 days","continuous","Catenary",null,null,null,null,null,null,null,null,null,null,"Catenary maintenance",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Sopron - Csorna","< >","Sopron","Csorna",2024,2024,24,25,"2024-06-10",null,"2024-06-17",null,"7 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Catenary maintenance and ballast tamping",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Zalaszentiván - Szombathely","< >","Zalaszentiván","Szombathely-Rendező",2024,2024,29,35,"2024-07-15",null,"2024-08-30",null,"46 days","continuous","Bridge","T",null,null,null,null,null,"R",null,null,null,"Bridge and catenary reconstruction",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Sopron - Csorna","< >","Sopron","Csorna",2024,2024,36,39,"2024-09-02",null,"2024-09-27",null,"25 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track and platform",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Szombathely - Csorna","< >","Porpác","Csorna",2024,2024,41,42,"2024-10-07",null,"2024-10-16",null,"9 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track and level crossing",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Csorna - Rajka","< >","Hegyeshalom","Rajka",2024,2024,42,42,"2024-10-17",null,"2024-10-19",null,"2 days","continuous","Track & Rail","T",null,null,null,null,null,"R",null,null,null,"Track and level crossing",null,null,null,"2023-12-15"]
[null,"GySEV/Raaberbahn",null,"Csorna - Rajka","< >","Csorna","Hegyeshalom",2024,2024,28,30,"2024-07-08",null,"2024-07-28",null,"20 days","continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,"Switch, signalling and catenary reconstruction",null,null,null,"2022-12-15"]
[null,"SŽ",791000,"Celje - Hodoš","< >","Ormož","Ivanjkovci",2024,2024,18,18,"2024-05-01","07:00:00","2024-05-03",0.79166666666666663,"2 days + 12 h 59 min","continuous","Maintenance","T",null,null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",791001,"Ljubljana - Celje","< >","Trbovlje","Trbovlje",2024,2024,16,38,"2024-04-15","07:00:00","2024-09-19",0.79166666666666663,"157 days + 12 h 59 min","continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,"station renewal",null,"N",null,"2023-12-13"]
[null,"SŽ",791002,"Ljubljana - Celje","< >","Litija","Litija",2024,2024,16,50,"2024-04-15","07:00:00","2024-12-15",0.79166666666666663,"244 days + 12 h 59 min","continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,"station renewal",null,"N",null,"2023-12-13"]
[null,"SŽ",791003,"Ljubljana - Celje","< >","Laze","Laze",2024,2024,3,17,"2024-01-19","08:00:00","2024-04-25",0.83333333333333304,"97 days + 12 h 0 min","continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,"station renewal",null,"N",null,"2023-12-13"]
[null,"SŽ",791004,"Ljubljana - Celje","< >","Laze","Ljubljana Zalog",2025,2025,27,33,"2025-07-05","09:00:00","2025-08-17",0.875,"43 days + 12 h 0 min","continuous","Track & Rail",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",793002,"Celje - Hodoš","< >","Dolga Gora","Poljčane",2024,2024,17,44,"2024-04-26","07:00:00","2024-11-03",0.79166666666666663,"191 days + 12 h 59 min","periodical","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"one track closed",null,"N",null,"2023-12-13"]
[null,"SŽ",795001,"Koper - Ljubljana","< >","Brezovica","Borovnica",2025,2025,1,14,"2025-01-01","07:00:00","2025-04-06",0.79166666666666663,"95 days + 12 h 59 min","continuous","Track & Rail",null,"LT",null,null,null,"C",null,"B",null,null,"left track closed",null,"N",null,"2023-12-13"]
[null,"SŽ",795002,"Koper - Ljubljana","< >","Logatec","Rakek",2024,2024,31,45,"2024-08-03","07:00:00","2024-11-10",0.79166666666666663,"99 days + 12 h 59 min","periodical","Track & Rail",null,"LT+ST",null,null,null,null,null,null,null,null,"right or left track closed",null,"N",null,"2023-12-13"]
[null,"SŽ",796001,"Koper - Ljubljana","< >","Divača","Koper",2024,2024,1,52,"2024-01-01","08:00:00","2024-12-31",0.75,"365 days + 10 h 0 min","periodical","Maintenance","T",null,null,null,null,null,null,null,null,null,"2x every month",null,"N",null,"2023-12-13"]
[null,"SŽ",795003,"Koper - Ljubljana","< >","Brezovica","Brezovica",2025,2025,1,14,"2025-01-01","07:00:00","2025-04-06",0.79166666666666663,"95 days + 12 h 59 min","continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,"station renewal",null,"N",null,"2023-12-13"]
[null,"SŽ",795004,"Koper - Ljubljana","< >","Preserje","Preserje",2025,2025,1,14,"2025-01-02","08:00:00","2025-04-06",0.83333333333333304,"94 days + 12 h 0 min","continuous","Track & Rail",null,null,null,null,null,null,null,null,null,null,"station renewal",null,"N",null,"2023-12-13"]
[null,"SŽ",795005,"Koper - Ljubljana","< >","Rakek","Postojna",2024,2024,36,38,"2024-09-07","07:00:00","2024-09-18",0.79166666666666663,"11 days + 12 h 59 min","continuous","Maintenance",null,"LT+ST",null,null,null,null,null,null,null,null,"left or right closed",null,"N",null,"2023-12-13"]
[null,"SŽ",795006,"Koper - Ljubljana","< >","Rakek","Postojna",2025,2025,33,34,"2025-08-15","07:00:00","2025-08-20",0.83333333333333304,"5 days + 13 h 59 min","continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",795007,"Koper - Ljubljana","< >","Rakek","Postojna",2025,2025,34,35,"2025-08-22","07:00:00","2025-08-25",0.875,"3 days + 14 h 59 min","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",795008,"Koper - Ljubljana","< >","Postojna","Prestranek",2025,2025,38,39,"2025-09-16","07:00:00","2025-09-22",0.91666666666666696,"6 days + 15 h 0 min","continuous","Maintenance",null,"LT+ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",795008,"Koper - Ljubljana","< >","Verd","Logatec",2025,2025,18,18,"2025-04-30","07:00:00","2025-05-05",0.91666666666666696,"5 days + 15 h 0 min","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",795006,"Koper - Ljubljana","< >","Pivka","Gornje Ležeče",2024,2024,27,30,"2024-07-01","07:00:00","2024-07-29",0.79166666666666663,"28 days + 12 h 59 min","continuous","Maintenance",null,"LT",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",795007,"Koper - Ljubljana","< >","Pivka","Gornje Ležeče",2025,2025,27,31,"2025-07-01","08:00:00","2025-07-29",0.83333333333333304,"28 days + 12 h 0 min","continuous","Maintenance",null,"ST",null,null,null,null,null,null,null,null,"maintenance",null,"N",null,"2023-12-13"]
[null,"SŽ",791001,"Koper - Ljubljana","< >","Ljubljana","Ljubljana",2023,2025,50,48,"2023-12-10","07:00:00","2025-11-30","19:00:00","721 days + 12 h 59 min","continuous","Track & Rail",null,null,null,null,null,"C",null,"B",null,null,"station renewal",null,"Y",null,45273]

{"sheet":"Graphic Overview","index":2,"n_rows":46,"n_cols":376,"rows_kept":46,"cut":false,"hidden":false,"merged":[[3,366,3,372],[3,373,3,374],[2,40,2,68],[2,69,2,99],[2,100,2,129],[2,130,2,160],[2,161,2,190],[2,191,2,221],[2,222,2,252],[2,253,2,282],[2,283,2,313],[2,314,2,343],[2,344,2,374],[3,37,3,43],[3,44,3,50],[3,324,3,330],[3,331,3,337],[3,338,3,344],[3,345,3,351],[3,352,3,358],[3,359,3,365],[3,289,3,295],[3,296,3,302],[3,303,3,309],[3,310,3,316],[3,317,3,323],[3,254,3,260],[3,261,3,267],[3,268,3,274],[3,275,3,281],[3,282,3,288],[3,219,3,225],[3,226,3,232],[3,233,3,239],[3,240,3,246],[3,247,3,253],[3,184,3,190],[3,191,3,197],[3,198,3,204],[3,205,3,211],[3,212,3,218],[3,149,3,155],[3,156,3,162],[3,163,3,169],[3,170,3,176],[3,177,3,183],[3,114,3,120],[3,121,3,127],[3,128,3,134],[3,135,3,141],[3,142,3,148],[3,79,3,85],[3,86,3,92],[3,93,3,99],[3,100,3,106],[3,107,3,113],[3,72,3,78],[3,9,3,15],[3,16,3,22],[3,23,3,29],[3,30,3,36],[0,1,1,7],[2,9,2,39],[3,51,3,57],[3,58,3,64],[3,65,3,71]]}
[null,"Baltic-Adriatic, Overview"]
[]
[null,null,null,null,null,null,2024,null,null,"January",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"March",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"April",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"May",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"June",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"July",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"August",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"September",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"October",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"November",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"December"]
[null,"Capacity Restriction","Type","Date from","Date to","Duration","IM",null,null,1,null,null,null,null,null,null,2,null,null,null,null,null,null,3,null,null,null,null,null,null,4,null,null,null,null,null,null,5,null,null,null,null,null,null,6,null,null,null,null,null,null,7,null,null,null,null,null,null,8,null,null,null,null,null,null,9,null,null,null,null,null,null,10,null,null,null,null,null,null,11,null,null,null,null,null,null,12,null,null,null,null,null,null,13,null,null,null,null,null,null,14,null,null,null,null,null,null,15,null,null,null,null,null,null,16,null,null,null,null,null,null,17,null,null,null,null,null,null,18,null,null,null,null,null,null,19,null,null,null,null,null,null,20,null,null,null,null,null,null,21,null,null,null,null,null,null,22,null,null,null,null,null,null,23,null,null,null,null,null,null,24,null,null,null,null,null,null,25,null,null,null,null,null,null,26,null,null,null,null,null,null,27,null,null,null,null,null,null,28,null,null,null,null,null,null,29,null,null,null,null,null,null,30,null,null,null,null,null,null,31,null,null,null,null,null,null,32,null,null,null,null,null,null,33,null,null,null,null,null,null,34,null,null,null,null,null,null,35,null,null,null,null,null,null,36,null,null,null,null,null,null,37,null,null,null,null,null,null,38,null,null,null,null,null,null,39,null,null,null,null,null,null,40,null,null,null,null,null,null,41,null,null,null,null,null,null,42,null,null,null,null,null,null,43,null,null,null,null,null,null,44,null,null,null,null,null,null,45,null,null,null,null,null,null,46,null,null,null,null,null,null,47,null,null,null,null,null,null,48,null,null,null,null,null,null,49,null,null,null,null,null,null,50,null,null,null,null,null,null,51,null,null,null,null,null,null,52]
[]
[null,"Jędrzejów - Sędziszów",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Tunel - Radom","continuous","2024-12-08","2025-12-08","133 days","PKP PLK-SA"]
[]
[null,"Radkowice - Wolica",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Tunel - Radom","continuous","2024-12-08","2026-06-10","364 days ","PKP PLK-SA"]
[]
[null,"Oświęcim - Nowy Bieruń",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Oświęcim - Katowice","continuous","2024-09-04","2025-01-31","97 days","PKP PLK-SA"]
[]
[null,"Čierna nad Tisou št. hr. - Varín",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Hidasnémeti - Košice ","periodical","2024-01-01","2024-11-30","334 days","ŽSR"]
[]
[null,"Nižná Myšľa - Ruskov",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","g"]
[null,"Section: Hidasnémeti - Košice ","periodical","2024-06-01","2025-12-31","578 days","ŽSR"]
[]
[null,"Košice -  Košice",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Hidasnémeti - Košice ","periodical","2024-01-01","2024-12-31","356 days","ŽSR"]
[]
[null,"Žilina - Žilina",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Žilina - Skalité","periodical","2024-01-01","2024-08-31","243 days","ŽSR"]
[]
[null,"Bratislava-Nové Mesto - Bratislava ÚNS",null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Rajka - Bratislava","periodical","2024-01-01","2024-03-31","90 days","ŽSR"]
[]
[null,"Hegyeshalom - Rajka",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Csorna - Rajka","continuous","2024-04-15","2024-04-30","15 days","GySEV/Raaberbahn"]
[]
[null,"Bősárkány - Jánossomorja",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Csorna - Rajka","continuous","2024-04-15","2024-04-30","15 days","GySEV/Raaberbahn"]
[]
[null,"Enese - Ikrény",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x"]
[null,"Section: Csorna - Komárom","continuous","2024-05-06","2024-05-09","3 days","GySEV/Raaberbahn"]
[]
[null,"Rábatamási - Kapuvár",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x"]
[null,"Section: Sopron - Csorna","continuous","2024-06-10","2024-06-14","4 days","GySEV/Raaberbahn"]
[]
[null,"Jánossomorja - Hegyeshalom",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Csorna - Rajka","continuous","2024-07-08","2024-07-28","20 days","GySEV/Raaberbahn"]
[]
[null,"Répcelak - Szil-Sopronnémeti",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x","x"]
[null,"Section: Szombathely - Csorna","continuous","2024-08-05","2024-11-30","117 days","GySEV/Raaberbahn"]

{"sheet":"Help","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Data","index":4,"n_rows":39,"n_cols":20,"rows_kept":39,"cut":false,"hidden":true,"merged":[]}
["IM",null,"Section",null,"Duration","ID value","Reason for restriction","Direction","Total Closure","Reduced Track Availability ","Speed Restrictions ","Weight, Length, Profile","Diesel only","Cancellation","Re-routing","Train replacement","Delays","Other","In yearly timetable","cancelled"]
["PKP PLK-SA",51,"Koper - Ljubljana",1,"continuous",11729,"Signal","< >","T","LT","S","W","D","C","R","B","D","O","Y","Y"]
["ŽSR",56,"Ljubljana - Celje",2,"periodical",null,"Switch",">",null,"ST",null,"L",null,null,null,null,null,null,"N","N"]
["MAV",55,"Celje - Hodoš",3,"periodical continuous",null,"Catenary","<",null,"LT+ST",null,"P"]
["GySEV/Raaberbahn",43,"Hodoš - Zalaszentiván",4,null,null,"Track & Rail",null,null,null,null,"W+L"]
["SŽ",79,"Zalaszentiván - Szombathely",5,null,null,"Tunnel",null,null,null,null,"W+P"]
[null,null,"Szombathely - Sopron",6,null,null,"Bridge",null,null,null,null,"L+P"]
[null,null,"Szombathely - Csorna",7,null,null,"Miscellaneous",null,null,null,null,"W+L+P"]
[null,null,"Sopron - Csorna",8,null,null,"Maintenance"]
[null,null,"Csorna - Komárom",9,null,null,"Others"]
[null,null,"Kelebia - Kiskunhalas",10]
[null,null,"Kiskunhalas - Budapest",11]
[null,null,"Budapest - Hatvan",12]
[null,null,"Kiskunhalas - Szolnok",13]
[null,null,"Szolnok - Hatvan",14]
[null,null,"Budapest - Komárom",15]
[null,null,"Komárom - Nové Zámky",16]
[null,null,"Csorna - Rajka",17]
[null,null,"Budapest -  Nové Zámky",18]
[null,null,"Hatvan - Miskolc",19]
[null,null,"Miskolc - Hidasnémeti",20]
[null,null,"Hidasnémeti - Košice ",21]
[null,null,"Rajka - Bratislava",22]
[null,null,"Bratislava - Leopoldov",23]
[null,null,"Nové Zámky - Leopoldov",24]
[null,null,"Leopoldov -  Žilina",25]
[null,null,"Žilina - Skalité",26]
[null,null,"Košice - Muszyna",27]
[null,null,"Muszyna - Kraków",28]
[null,null,"Skalité - Oświęcim",29]
[null,null,"Oświęcim - Kraków",30]
[null,null,"Oświęcim - Katowice",31]
[null,null,"Katowice - Tunel",32]
[null,null,"Kraków - Tunel",33]
[null,null,"Tunel - Radom",34]
[null,null,"Radom - Dęblin",35]
[null,null,"Dęblin - Małaszewicze",36]
[null,null,"Dęblin - Warszawa",37]
[null,null,"Radom - Warszawa",38]

{"sheet":"Map_Backup","index":5,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}